## 敏捷项目 Product Backlog 规划
Story ID | Story Name | Description (User Story Format) | Priority (MoSCoW) | Iteration (Sprint) number | Acceptance Criteria | Estimate (Story Points) | Notes (Epic & Remarks) | Date started (or planned) | Date finished (or planned)
NFR-01 | Setup Local Storage | As a system, I want to use text files (CSV/JSON/XML) to store all data, so that the system runs persistently without a database. | Must have | 1 | 1. The verification system can create and read/write data files locally. 2. After the verification program restarts, user information and position information remain intact. | 8 | Epic: System (NFR) | 2026-03-22 | 2026-03-25
NFR-02 | Web Application Runtime Environment Compatibility | As a system development and maintenance team, I want the system to be compatible with mainstream server runtime environments, so that the system can be stably deployed and run in the college's standard server environment. | Must have | 1 | 1. The system is developed based on Java Servlet/JSP specification, fully compatible with Apache Tomcat 8.5+ stable versions2. The system is fully compatible with Java 8 and above LTS versions, no additional advanced framework dependencies (such as Spring Boot) are required3. The system supports deployment on mainstream server operating systems: Windows Server 2016+, CentOS 7+, Ubuntu 18.04+4. The system can be deployed and started normally with standard Tomcat deployment steps, no additional complex configuration is required | 5 | Epic: System (NFR) | 2026-03-22 | 2026-03-25
NFR-03 | Code Modularity & Maintainability | As a system development team, I want the system code to adopt a modular and layered design, so that the code is easy to maintain, iterate and expand, and meets the software engineering specifications. | Must have | 1，2，3，4 | 1. The code adopts a standard MVC layered architecture adapted to Servlet/JSP, separating the view layer, control layer, and business logic layer2. The code is modularly designed, with low coupling between modules, and a single module modification will not affect other unrelated modules3. The core business code has complete JavaDoc annotations, and the code logic is clear and conforms to Java development specifications4. The file read/write, data parsing, permission verification and other general logic are encapsulated into public tool classes to avoid duplicate code | 5 | Epic: System (NFR) | 2026-03-22 | 2026-05-24
NFR-04 | System Error Prompt Usability | As an end user, I want the system to give clear and easy-to-understand error prompts when an operation exception occurs, so that I can know the reason for the error and how to correct it. | Must have | 1，2，3，4 | 1. All error prompts in the system use clear and easy-to-understand language, avoiding professional jargon that users cannot understand2. The error prompt clearly indicates the cause of the error and the specific operation method for correction3. The system distinguishes between operation prompts, success prompts, warning prompts and error prompts, with clear visual distinction4. No ambiguous error prompts such as "operation failed" without specific reasons | 3 | Epic: System (NFR) | 2026-03-22 | 2026-05-24
US-01 | User Registration | As a new user, I want to register as a TA, MO, or Admin, so that I can access the system with appropriate role permissions. | Must have | 1 | 1. Verify that users can select roles and submit registration information. 2. The verification system will reject existing student numbers/employee IDs. 3. The verification password cannot be empty. | 5 | Epic: User Mgt | 2026-03-26 | 2026-03-30
US-02 | User Login & Auth | As a registered user, I want to log in securely, so that I am directed to the correct dashboard based on my role. | Must have | 1 | 1. Inputting the correct vouchers [account and non-plaintext password] will enable successful login. 2. Incorrect password verification will provide a clear prompt. 3. TA, MO and Admin will see different interfaces after logging in. | 5 | Epic: User Mgt | 2026-03-26 | 2026-03-30
TA-01 | Manage TA Profile | As a TA, I want to create and update my user profile (including my basic information, skill tags and CV path), so that I have a reusable resume in the system. | Must have | 1 | 1. Verify that after logging in, TA can fill in and update basic information [name, age, student number of the college, relevant course grades, contact information. The system marks the required fields and prompts the user to complete them before saving]. Also, verify the skills tags, relevant experience, and resume path. 2. Verify and remind that the Profile data has been successfully saved. | 13 | Epic: TA Profile | 2026-03-31 | 2026-04-03
TA-02 | View & Filter Vacancies | As a TA applicant, I want to view available vacancies and filter them by module code or course name, so that I can quickly find suitable roles. | Must have | 2 | 1. Verify that TA can view all open positions [display core information, including course name, job requirements, number of recruits, application deadline, etc.]. 2. Verify that the filtering search function is working properly. 3. Verify that the remaining positions and other information are displayed correctly. | 13 | Epic: Vacancy Mgt.Adding the Filter function enhances usability. | 2026-04-04 | 2026-04-07
TA-03 | Submit Application | As a TA applicant, I want to apply for a job using my saved profile by clicking the "Apply" button, so that the MO can review my qualifications without me re-entering data. And The specific administrator can view my resume. | Must have | 2 | 1. After the TA clicks the application, it will be displayed that the submission is successful and the Profile will be automatically associated with the corresponding MO. 2. Verify that the status of the record changes to "Pending". | 5 | Epic: Application Process | 2026-04-08 | 2026-04-09
TA-04 | Track Status | As a TA applicant, I want to see the status of all my past and current applications in one dashboard, so that I don't have to guess the outcomes. | Must have | 2 | Verify that the dashboard accurately categorizes and displays the records as Pending, Accepted, and Rejected. | 3 | Epic: Application Process | 2026-04-10 | 2026-04-11
MO-01 | Post TA Vacancy | As an MO, I want to create a TA vacancy (including module code,Course name, job requirements, number of positions to be filled, required skills, job responsibilities, working hours, application deadline) or an activity (e.g., invigilation), so that I can recruit for different needs.. | Must have | 3 | 1. The verification process can only allow the MO to post positions for the modules assigned to him/her, and fill in the required fields of the position description, etc. 2. The posted positions will be immediately synchronized to the "hall" section of the system. | 5 | Epic: Vacancy Mgt | 2026-04-12 | 2026-04-15
MO-02 | Delate and Edit TA Vacancy | As a MO, I edit the published positions and close them when necessary to facilitate flexible management of the recruitment positions. | Must have | 3 | 1. Before the application deadline, the person in charge can edit the content of the published positions. After saving, the modified content will be updated synchronously. 2. The person in charge can manually close the published positions at any time. After closing, the positions will no longer be displayed in the position hall and new applications will be prohibited. | 5 | Epic: Vacancy Mgt | 2026-04-16 | 2026-04-18
MO-03 | Review Applicants | As an MO, I want to view a list of all TAs who applied for my modules, so that I can evaluate their CVs and details. | Must have | 3 | 1. Verify that MO only sees the list of applicants for their own module. 2. Verify that clicking on the list can display the complete personal profile and CV of the TA. 3. Review the qualifications and make an evaluation. 4. The person in charge can overview the status of the applicants for this module, including those who are pending review, have been shortlisted, have been hired, or have been rejected. | 8 | Epic: Application Process | 2026-04-19 | 2026-04-23
AD-01 | Lobby Business Management | As an admin, it is necessary to monitor whether the position section in the hall can be updated and cleared normally. | Should have | 3 | 1. The positions successfully created by MO and published before the deadline are displayed normally on the hall. 2. After being published on the hall, the positions that have reached the deadline are removed. 3. After clicking "Accepted" for position verification, the available quota for this position decreases by 1; when the verification quota is 0, the position automatically becomes closed and the job information on the hall is deleted. | 13 | Epic: Admin Oversight | 2026-04-24 | 2026-04-29
AD-02 | Admin Dashboard & Reports | As an Admin, I want to view a high-level summary (total vacancies, total applications, filled roles), so that I can monitor recruitment progress. | Should have | 3 | 1. Verify that the Admin interface can dynamically calculate and display the total of each item. 2. Verify that the Admin can view the activity status of all users. | 8 | Epic: Admin Oversight | 2026-04-30 | 2026-05-03
AD-03 | Admin Workload Report | As an Admin, I want to view a list of all hired TAs and their total accumulated working hours, so that I can monitor the overall school workload. | Must have | 4 | 1. Verify that the Admin panel can aggregate and calculate the total working hours for each TA. 2. Verify that it can be sorted from the highest to the lowest based on workload. | 5 | Epic:Workload | 2026-05-04 | 2026-05-06
AD-04 | Workload Constraint | As a system, I want to prevent a TA from being 'Accepted' if it causes them to exceed 20 working hours, so that workload regulations are respected. | Should have | 4 | When the total duration of TA exceeds 20 hours, MO cannot accept it and the system will issue a warning to TA. | 5 | Epic: Workload | 2026-05-07 | 2026-05-09
AI-01 | Identify Missing Skills | As a TA, I want AI to analyze my profile against a job and identify missing skills, so that I can know what to improve for future applications. | Could have | 4 | 1. Verify that TA can click on "AI Analysis" when viewing the job details. 2. Verify that the AI can return a piece of text clearly indicating the specific skills that are missing. | 8 | AI Feature:Improve user experience. | 2026-05-10 | 2026-05-15
AI-02 | AI Workload Balancing | As an Admin, I want AI to analyze the school's workload distribution and suggest reallocations if some TAs are over-utilized, so that we balance the workload fairly. | Want to have | 4 | 1. Verify that the AI can read all of TA's workload data. 2. Verify that the AI can generate a load balancing optimization suggestion. | 13 | AI Feature:This is a high-level exploration and its priority has been lowered. | 2026-05-16 | 2026-05-19
AI-03 | AI Skill Matching | As an MO, I want to use an AI tool to match applicants' skills with my job requirements, so that I can quickly identify the most suitable candidates. | Could have | 4 | 1. The verification system can call the AI interface to compare the TA Profile and the Job Description. 2. The verification system can output a match score ranging from 0 to 100. | 8 | AI Feature:The structured prompt needs to be processed. | 2026-05-20 | 2026-05-24