## 表格_20260312 (1)
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
System Core Module
SYS-001 | Unified User Login & Role-Based Access Control | As a system user (TA Applicant/Module Organiser/Admin), I want to log in to the system with my unique account and password, and get role-matched function permissions, so that I can securely access the functions corresponding to my identity. | P0-Must Have | 1 | 1. The system provides a unified web login entrance, supporting input of unique account (student ID/employee ID) and password2. The system verifies account and password, and returns clear error prompts for incorrect information3. After successful login, the system automatically identifies the user role (TA/MO/Admin) and redirects to the corresponding role homepage4. Strict permission isolation is implemented: users can only access function modules corresponding to their roles, and cross-role unauthorized access is prohibited5. The system provides a secure logout function, which clears the user's session and returns to the login page after logout | 3 | Core underlying function, basis for all system operations, adapted to Java Web Servlet session management | 2026-03-13 | 2026-03-18
SYS-002 | User Password Encryption & Reset | As a system user, I want my password to be stored securely and be able to reset my password when I forget it, so that I can protect my account security and regain account access. | P0-Must Have | 1 | 1. All user passwords are encrypted and stored in text files, plaintext password storage is strictly prohibited2. The system provides a password reset entrance on the login page, supporting password reset by verifying unique account and registered email3. The system verifies the matching of account and registered email, and gives error prompts for mismatched information4. After successful verification, the user can set a new password, and the system synchronously updates the encrypted password in the storage file | 2 | Basic security requirement for web application account management | 2026-03-15 | 2026-03-20
SYS-003 | Input Data Validation & Exception Handling | As a system user, I want the system to verify my input data and give clear exception prompts, so that I can correct incorrect input in time and avoid system errors caused by invalid data. | P0-Must Have | 1 | 1. The system performs mandatory format validation on all user input fields, including student ID/employee ID, email, date, number, etc.2. Clear error prompts are given when input does not meet format requirements, indicating the error reason and correction rules3. The system handles exceptions such as file read/write failure, data format error, and concurrent operation conflict, with friendly prompts and no system crash4. Mandatory fields are set for all core business forms, which cannot be saved or submitted if not completed | 3 | Basic guarantee for stable operation of the web application, covering all business modules | 2026-03-13 | 2026-03-20
SYS-004 | In-System Notification Center | As a system user, I want to receive and view system notifications in the message center, so that I can timely learn about key business changes such as application status updates and job status changes. | P1-Should Have | 2 | 1. The system automatically generates notification messages when key business status changes, and associates them with the corresponding user2. Users can view all received messages in the message center, including title, content, generation time, and read/unread status3. Users can mark messages as read or delete messages, and the number of unread messages is displayed on the homepage | 2 | Improve user experience and information timeliness | 2026-03-25 | 2026-04-01
TA Applicant Module
TA-001 | TA Applicant Account Registration | As a TA applicant, I want to register a system account with my student information, so that I can create my application profile and use the recruitment functions. | P0-Must Have | 1 | 1. The system provides a web registration page for TA applicants, supporting input of unique student ID, full name, valid college email, password and confirm password2. The system verifies the uniqueness of student ID and email, and gives clear error prompts for duplicates3. The system verifies that the password meets security rules (minimum 6 characters, including letters and numbers)4. After successful registration, the system stores the encrypted account information in a text file, and prompts the user to log in | 2 | Entry function for TA applicants, meets the core requirement of "create applicant profile" | 2026-03-13 | 2026-03-18
TA-002 | TA Applicant Profile Creation & Editing | As a TA applicant, I want to create and edit my personal application profile, so that I can show my academic background, skills and experience to module organisers. | P0-Must Have | 1 | 1. After logging in, applicants can enter the profile editing page, fill in and modify personal information including academic background, course scores, professional skills, relevant experience, and contact information2. The system marks mandatory fields, and prompts users to complete them before saving3. The edited profile is saved and stored in a text file associated with the user's account4. Applicants can view the complete saved profile at any time | 2 | Core function for TA application, meets the core requirement of "create applicant profile" | 2026-03-16 | 2026-03-20
TA-003 | TA Resume Upload & Management | As a TA applicant, I want to upload and manage my resume files, so that module organisers can view my detailed resume when reviewing my application. | P0-Must Have | 1 | 1. The system supports applicants to upload resume files in common formats (txt/pdf/doc), with a reasonable file size limit2. Uploaded resume files are associated with the applicant's account, and the file information is stored in a text file3. Applicants can view, replace or delete their uploaded resumes4. The system gives clear prompts for upload failure caused by format or size issues | 2 | Meets the core requirement of "upload CV" | 2026-03-18 | 2026-03-21
TA-004 | Available Job Post Query & View | As a TA applicant, I want to view all open TA job posts and their detailed information, so that I can find suitable positions to apply for. | P0-Must Have | 1 | 1. After logging in, applicants can view the list of all open job posts, displaying key information including module name, job type, recruitment number, and application deadline2. The system automatically hides job posts that have passed the application deadline or been closed3. Applicants can click a job post to view the full detailed information of the position4. The system marks job posts that the applicant has already applied for | 2 | Meets the core requirement of "find available jobs" | 2026-03-18 | 2026-03-21
TA-005 | TA Job Application Submission | As a TA applicant, I want to submit an application for a target job post, so that the module organiser can review my application materials. | P0-Must Have | 1 | 1. Applicants can click the "Apply" button on the job detail page to submit an application2. Before submission, the system verifies that the applicant has completed the core profile, otherwise prompts to complete the information first3. After successful submission, the system generates a unique application record, associates the applicant's profile and resume with the job, and stores the data in a text file4. The system prohibits repeated applications for the same job post from the same applicant5. After successful submission, the application status is updated to "Pending Review" | 2 | Meets the core requirement of "apply for jobs" | 2026-03-20 | 2026-03-23
TA-006 | TA Application Status Query | As a TA applicant, I want to view all my submitted applications and their real-time status, so that I can keep track of the progress and results of my applications. | P0-Must Have | 2 | 1. Applicants can enter the "My Applications" page to view the list of all application records2. The application list displays key information including job name, application time, latest status, and last update time3. Applicants can click an application record to view the detailed information and full status change history4. The system supports filtering applications by status (Pending Review/Shortlisted/Accepted/Rejected) | 2 | Meets the core requirement of "check application status" | 2026-03-25 | 2026-03-30
TA-007 | Job Post Filter & Search | As a TA applicant, I want to filter and search job posts, so that I can quickly find the positions that match my needs. | P1-Should Have | 2 | 1. The system supports keyword search for job posts, matching module name, job requirements and other content2. The system supports filtering job posts by job type (module TA/invigilation) and application deadline3. The job list is updated in real time according to the search and filter conditions | 2 | Improve the efficiency of job hunting for applicants | 2026-03-28 | 2026-04-02
Module Organiser (MO) Module
MO-001 | MO Account Permission Management | As a Module Organiser, I want to log in to the system with my assigned account and get the corresponding management permissions, so that I can complete the TA recruitment management work. | P0-Must Have | 1 | 1. MO can log in to the system normally with the assigned account and password, and enter the MO exclusive management homepage2. The system strictly controls MO's permissions: MO can only manage the job posts created by themselves, and cannot operate the jobs of other MOs3. MO can modify their personal basic information and login password | 1 | Basis for MO to use recruitment management functions | 2026-03-15 | 2026-03-20
MO-002 | TA Recruitment Job Post Creation & Publishing | As a Module Organiser, I want to create and publish TA recruitment job posts, so that TA applicants can view the job information and apply for the position. | P0-Must Have | 1 | 1. MO can enter the job creation page, fill in the full job information including module name, job type, recruitment number, required skills, job responsibilities, working hours, and application deadline2. The system marks mandatory fields, and the job cannot be published if mandatory fields are not completed3. MO can save the unfinished job as a draft, and continue to edit, delete or publish the draft later4. After clicking publish, the job status is updated to "Open", and is visible to all TA applicants in the job hall | 3 | Meets the core requirement of "post jobs" | 2026-03-16 | 2026-03-20
MO-003 | Published Job Editing & Closing | As a Module Organiser, I want to edit the published job posts and close the jobs when needed, so that I can flexibly manage the job posts. | P0-Must Have | 2 | 1. Before the application deadline, MO can edit the content of the published job post, and the modified content is updated synchronously after saving2. MO can manually close the published job post at any time. After closing, the job is no longer displayed in the job hall, and new applications are prohibited3. The system automatically closes the job post when the application deadline is reached | 2 | Core function of job life cycle management | 2026-03-23 | 2026-03-30
MO-004 | Job Application List & Applicant Material Review | As a Module Organiser, I want to view the list of applicants for my published jobs and their complete application materials, so that I can review the applicants' qualifications. | P0-Must Have | 2 | 1. MO can view the list of all published jobs, with real-time display of the number of applicants for each job2. MO can click into a job post to view the full list of applicants, displaying key information of each applicant3. MO can click an applicant to view their complete profile, uploaded resume, and application remarks4. MO can add review remarks for applicants, which are only visible to themselves | 2 | Basis for MO to complete applicant screening | 2026-03-23 | 2026-03-30
MO-005 | Applicant Screening & Application Status Update | As a Module Organiser, I want to update the application status of applicants, so that I can complete the recruitment selection and inform applicants of the review results. | P0-Must Have | 2 | 1. MO can update the application status for a single applicant, including Pending Review, Shortlisted, Accepted, Rejected2. The system supports batch update of application status for multiple applicants to improve review efficiency3. After the status is updated, the system synchronously updates the application record and notifies the corresponding applicant4. The system counts the number of accepted applicants, and gives a prompt when the number reaches the planned recruitment quota | 2 | Meets the core requirement of "select applicants for jobs" | 2026-03-25 | 2026-04-01
Admin Module
ADM-001 | Admin Account & Super Permission Management | As a system Admin, I want to log in to the system with the admin account and get super management permissions, so that I can complete system management and business supervision work. | P0-Must Have | 1 | 1. Admin can log in to the system with the exclusive admin account, and enter the admin exclusive management homepage2. The system grants the highest level of management permissions to the admin account, including user account management, business supervision, and system data management3. Admin can modify the login password and basic information of the admin account | 1 | Basis for admin to perform system management functions | 2026-03-15 | 2026-03-20
ADM-002 | TA Overall Workload Query & Supervision | As a system Admin, I want to query and check the overall workload of all TAs, so that I can avoid excessive workload of a single TA and ensure the rationality of TA arrangement. | P0-Must Have | 2 | 1. The system summarizes the total workload of each TA based on all accepted and confirmed job posts, including the number of served modules/activities and total working hours2. Admin can view the workload list of all TAs, with detailed workload data of each TA3. Admin can search and filter TAs by student ID, name, major, etc., to quickly locate the target TA4. The system supports setting a workload threshold, and automatically marks TAs whose workload exceeds the threshold with early warning prompts | 3 | Meets the core requirement of "Admin can check TA’s overall workload" | 2026-03-30 | 2026-04-10
ADM-003 | Full User Account Management | As a system Admin, I want to manage all user accounts in the system, so that I can maintain the normal operation of the system and standardize account permissions. | P1-Should Have | 2 | 1. Admin can view the full list of all user accounts (TA/MO/Admin), including account ID, user name, role, creation time, and account status2. Admin can create MO and admin accounts, assign corresponding roles and permissions3. Admin can enable or disable user accounts, and reset passwords for users when needed | 3 | Core system operation and maintenance function | 2026-03-30 | 2026-04-08
AI Optional Function Module
AI-001 | Job-Applicant Skill Matching & Scoring | As a Module Organiser, I want to get the skill matching score between the job requirements and applicants, so that I can quickly screen suitable applicants and improve review efficiency. | P2-Could Have | 3 | 1. The system extracts required skill tags from the job post and mastered skill tags from the applicant's profile2. The system calculates the matching degree score between the applicant and the job based on skill matching, academic experience and working time matching3. The matching score is displayed in the applicant list, and supports sorting by matching score4. The system provides a clear explanation of the calculation basis of the matching score to ensure result explainability | 4 | Optional AI-powered feature mentioned in the handout, implemented with rule-based logic to comply with technical constraints | 2026-04-10 | 2026-04-25
AI-002 | Applicant Missing Skill Identification | As a TA applicant, I want to know the missing skills for the target job post, so that I can understand the gap between myself and the job requirements. | P2-Could Have | 3 | 1. The system compares the applicant's mastered skills with the required skills of the target job, and identifies the missing required skills2. The system clearly displays the list of missing skills and the overall matching degree prompt to the applicant3. The explanation of the skill gap is clear and easy to understand | 2 | Optional AI-powered feature mentioned in the handout | 2026-04-15 | 2026-04-28
AI-003 | TA Workload Balancing Recommendation | As an Admin, I want to get workload balancing recommendations for TAs, so that I can avoid excessive workload of individual TAs and ensure fair TA arrangement. | P2-Could Have | 4 | 1. The system identifies TAs with excessive workload and TAs with insufficient workload based on the overall workload data2. The system provides reasonable workload adjustment recommendations for the admin3. The system clearly explains the basis of the recommendations to ensure result explainability | 3 | Optional AI-powered feature mentioned in the handout | 2026-05-04 | 2026-05-15
No-functional Requirements Module
NFR-001 | Web Application Runtime Environment Compatibility | As a system development and maintenance team, I want the system to be compatible with mainstream server runtime environments, so that the system can be stably deployed and run in the college's standard server environment. | P0-Must Have | 1 | 1. The system is developed based on Java Servlet/JSP specification, fully compatible with Apache Tomcat 8.5+ stable versions | 1 | Core environmental constraint, must be defined before development starts, complies with the mandatory technical requirements of the project | 2026-03-13 | 2026-03-15
2. The system is fully compatible with Java 8 and above LTS versions, no additional advanced framework dependencies (such as Spring Boot) are required
3. The system supports deployment on mainstream server operating systems: Windows Server 2016+, CentOS 7+, Ubuntu 18.04+
4. The system can be deployed and started normally with standard Tomcat deployment steps, no additional complex configuration is required
NFR-002 | Client Browser Compatibility | As an end user (TA/MO/Admin), I want the system to be compatible with mainstream browsers, so that I can access and use the system normally through common browsers without additional software installation. | P0-Must Have | 1 | 1. The system page and functions are fully compatible with the latest 3 versions of mainstream browsers: Google Chrome, Microsoft Edge, Mozilla Firefox | 2 | Basic usability requirement, affects all end users' access experience | 2026-03-16 | 2026-03-20
2. There is no page layout disorder, function failure, or interactive exception in compatible browsers
3. The page display is adaptive to mainstream desktop screen resolutions (19201080, 1366768)
NFR-003 | System Operation Response Performance | As a system user of any role, I want the system to respond to my operations quickly, so that I can complete the business operations efficiently without long waiting. | P1-Should Have | 1 | 1. For single-user operations, the response time of page jumps, data queries, and form submissions does not exceed 2 seconds | 2 | Core performance requirement, affects the overall user experience of the system | 2026-03-16 | 2026-03-22
2. For file upload operations (resume upload), the response time does not exceed 5 seconds for files within the size limit
3. The system gives real-time feedback for loading operations, avoiding unresponsive pages
NFR-004 | Concurrent User Access Support | As a system admin and end user, I want the system to support multi-user concurrent access, so that multiple users can operate the system at the same time without data conflict or system exception. | P1-Should Have | 2 | 1. The system supports at least 50 concurrent users operating the system at the same time | 3 | Critical performance requirement for web applications, avoids data errors in multi-user scenarios | 2026-03-23 | 2026-04-01
2. Under concurrent access, there is no data overwriting, file read/write conflict, or data loss in core business operations
3. Under concurrent access, the response time of core business operations does not exceed 3 seconds
4. The system implements a reasonable file locking mechanism for concurrent text file read/write operations
NFR-005 | User Password Secure Encrypted Storage | As a system user of any role, I want my login password to be stored securely, so that I can protect the security of my account and personal information, and avoid password leakage. | P0-Must Have | 1 | 1. All user passwords are encrypted using a reversible encryption algorithm before being stored in the text file | 1 | Mandatory security requirement, related to the account security of all users | 2026-03-13 | 2026-03-18
2. Plaintext password storage is strictly prohibited in any system files or logs
3. The password encryption and decryption logic is stable, and the user can log in normally with the correct password after encryption
NFR-006 | Role-Based Permission Isolation Control | As a system admin, I want the system to implement strict permission isolation between different roles, so as to prevent unauthorized cross-role access and data tampering, and ensure system data security. | P0-Must Have | 1 | 1. The system implements a strict RBAC (Role-Based Access Control) mechanism, with three roles: TA Applicant, Module Organiser, Admin | 3 | Core security requirement, the basis of system permission management, complies with the business role design | 2026-03-13 | 2026-03-20
2. Users can only access the function modules and data corresponding to their roles, and cannot access cross-role pages or functions through URL jumping or other unauthorized operations
3. The system verifies the user's role and permission for every backend business request, and rejects unauthorized requests
NFR-007 | Web Session Security & Timeout Control | As a system user of any role, I want my login session to have a security timeout mechanism, so as to prevent unauthorized access to my account when I leave the device without logging out. | P1-Should Have | 1 | 1. The system sets a reasonable session timeout period (30 minutes by default), and the session will automatically expire if there is no operation for a long time | 1 | Basic web application security requirement, protects user account security | 2026-03-15 | 2026-03-20
2. After the session expires, the system automatically redirects to the login page, and prohibits accessing any business functions before re-login
3. The session is cleared immediately after the user logs out, to prevent session hijacking
NFR-008 | User Input Data Validation & Exception Handling | As a system development and maintenance team, I want the system to perform strict validation on all user input and complete exception handling, so as to avoid system exceptions, data corruption or security risks caused by invalid or malicious input. | P0-Must Have | 1 | 1. The system performs mandatory format and legality validation on all user input fields at the front end and back end, including student ID, email, date, number, text content, etc. | 3 | Mandatory stability and security requirement, runs through all business modules | 2026-03-13 | 2026-03-20
2. The system gives clear and friendly error prompts for invalid input, indicating the error reason and correction rules
3. The system handles exceptions such as file read/write failure, data format error, and network exception, without page crash or system downtime
4. The system prevents malicious input attacks such as XSS through input validation and output escaping
NFR-009 | System Operation Log Audit | As a system admin, I want the system to record the key operation logs of all users, so that I can trace the operation history, troubleshoot problems, and meet the audit requirements. | P1-Should Have | 2 | 1. The system automatically records key operations of all users, including user account, operation type, operation content, operation time, operation IP, and operation result | 2 | System security and audit requirement, convenient for problem tracing and responsibility confirmation | 2026-03-25 | 2026-04-05
2. The operation log is stored in a separate text file, which cannot be modified or deleted by non-admin users
3. The admin can filter and search operation logs by user account, operation time range, and operation type
4. The log content is complete and traceable, covering all key business operations and permission changes
NFR-010 | Business Data Persistence & Reliability | As a system user of any role, I want the data generated by my operations to be stored reliably, so that the data will not be lost after system restart or exception, and the business data is consistent and complete. | P0-Must Have | 1 | 1. All business data generated by user operations (account information, profile, job posts, application records, etc.) are persisted to the corresponding text files in real time after the operation is completed | 2 | Core reliability requirement, ensures the security and integrity of all system business data | 2026-03-13 | 2026-03-20
2. The system ensures the integrity of data writing, and there will be no incomplete data or file corruption caused by write interruption
3. After the system is restarted, all historical business data can be read and loaded normally without loss
4. The data storage format complies with the project requirements, only using standard text formats (JSON/CSV/XML/TXT), no database is used
NFR-011 | System Data Backup & Recovery Function | As a system admin, I want to back up and restore the full data of the system, so as to prevent data loss caused by misoperation, file damage or system exception, and ensure data security. | P1-Should Have | 3 | 1. The system supports one-click manual backup of all system data files, and the backup files are named with time stamps for easy identification | 2 | Data security requirement, reduces the risk of permanent data loss | 2026-04-10 | 2026-04-20
2. The system supports setting automatic backup at fixed intervals (e.g. daily backup)
3. The admin can select historical backup files to restore the system data with one click
4. Before data recovery, the system automatically backs up the current data to avoid data loss caused by recovery failure
NFR-012 | Applicant Privacy Data Access Control | As a TA applicant, I want my personal privacy data to be strictly protected, so that only authorized personnel can view my information, and my personal privacy is not leaked. | P1-Should Have | 1 | 1. The applicant's personal profile, academic information, and uploaded resume are only visible to the MO who published the job applied by the applicant and the system admin | 1 | Privacy protection requirement, complies with the college's information security management rules | 2026-03-16 | 2026-03-20
2. Other MOs or ordinary users cannot access the applicant's privacy data through any operations
3. The applicant's privacy data is not displayed in any public list or page, and is only displayed in the authorized business scenario
NFR-013 | Code Modularity & Maintainability | As a system development team, I want the system code to adopt a modular and layered design, so that the code is easy to maintain, iterate and expand, and meets the software engineering specifications. | P1-Should Have | 1 (runs through all iterations) | 1. The code adopts a standard MVC layered architecture adapted to Servlet/JSP, separating the view layer, control layer, and business logic layer | 3 | Non-functional requirement related to project delivery, meets the course's focus on software engineering principles | 2026-03-13 | 2026-05-20
2. The code is modularly designed, with low coupling between modules, and a single module modification will not affect other unrelated modules
3. The core business code has complete JavaDoc annotations, and the code logic is clear and conforms to Java development specifications
4. The file read/write, data parsing, permission verification and other general logic are encapsulated into public tool classes to avoid duplicate code
NFR-014 | System Error Prompt Usability | As an end user, I want the system to give clear and easy-to-understand error prompts when an operation exception occurs, so that I can know the reason for the error and how to correct it. | P1-Should Have | 1 (runs through all iterations) | 1. All error prompts in the system use clear and easy-to-understand language, avoiding professional jargon that users cannot understand | 1 | Usability requirement, improves the user's operation experience | 2026-03-16 | 2026-04-10
2. The error prompt clearly indicates the cause of the error and the specific operation method for correction
3. The system distinguishes between operation prompts, success prompts, warning prompts and error prompts, with clear visual distinction
4. No ambiguous error prompts such as "operation failed" without specific reasons