## 敏捷项目 Product Backlog 规划
Story ID | Story Name | Description (User Story Format) | Priority (MoSCoW) | Iteration (Sprint) number | Acceptance Criteria | Estimate (Story Points) | Notes (Epic & Remarks) | Date started (or planned) | Date finished (or planned)
US-01 | Setup Local Storage | As a system, I want to use text files (CSV/JSON/XML) to store all data, so that the system runs persistently without a database. | Must have | 1 | 1. 验证系统能在本地创建并读写数据文件。2. 验证程序重启后，用户信息和岗位信息依然存在。 | 13 | Epic: System (NFR)非功能性需求作为故事点 。
US-02 | User Registration | As a new user, I want to register as a TA, MO, or Admin, so that I can access the system with appropriate role permissions. | Must have | 1 | 1. 验证用户可选择角色并提交注册信息。2. 验证系统会拒绝已存在的学号/工号。3. 验证密码不能为空。 | 5 | Epic: User Mgt
US-03 | User Login & Auth | As a registered user, I want to log in securely, so that I am directed to the correct dashboard based on my role. | Must have | 1 | 1. 验证输入正确的凭证可成功登录。2. 验证 TA、MO 和 Admin 登录后看到不同的界面。3. 验证错误密码会有明确提示。 | 5 | Epic: User Mgt
US-04 | Manage TA Profile | As a TA, I want to create and update my user profile (including my basic information, skill tags and CV path), so that I have a reusable resume in the system. | Must have | 1 | 1. 验证 TA 登录后可以填写并更新基本信息、技能标签和简历路径。2. 验证 Profile 数据成功保存。 | 8 | Epic: User Mgt
US-05 | Module Assignment | As an Admin, I want to create academic modules and assign them to specific MOs, so that MOs are authorized to post vacancies for them. | Must have | 1 | 1. 验证 Admin 可以输入模块代码和名称。2. 验证只能将模块分配给已注册的 MO。3. 验证分配关系成功保存。 | 8 | Epic: Admin Oversight逻辑严密的拓展功能。
US-06 | Post TA Vacancy | As an MO, I want to create a TA vacancy (including module code, job description, required skills, and slots) or an activity (e.g., invigilation), so that I can recruit for different needs.. | Must have | 2 | 1. 验证 MO 只能为分配给自己的模块发布岗位。2. 验证发布的岗位立即同步到系统的“大厅”中。 | 5 | Epic: Vacancy Mgt
US-07 | View & Filter Vacancies | As a TA applicant, I want to view available vacancies and filter them by module code, so that I can quickly find suitable roles. | Must have | 2 | 1. 验证 TA 能看到所有处于开放状态的岗位。2. 验证过滤搜索功能正常工作。3. 验证岗位的剩余名额显示正确。 | 5 | Epic: Vacancy Mgt增加 Filter 功能提升可用性。
US-08 | Submit Application | As a TA applicant, I want to apply for a job using my saved profile, so that the MO can review my qualifications without me re-entering data. | Must have | 2 | 1. 验证 TA 点击申请后，自动关联其 Profile。 2. 验证记录状态变为 "Pending"。 | 5 | Epic: Application Process
US-09 | Review Applicants | As an MO, I want to view a list of all TAs who applied for my modules, so that I can evaluate their CVs and details. | Must have | 2 | 1. 验证 MO 只看到自己模块的申请者列表。2. 验证点击列表可展示 TA 的完整个人档案和 CV。 | 8 | Epic: Application Process涉及多表数据联查，估分较高。
US-10 | Make Decision | As an MO, I want to mark an application as 'Accepted' or 'Rejected', so that the TA is notified and the vacancy slots are updated. | Must have | 3 | 1. 验证点击 Accepted 后，该岗位可用名额减 1。2. 验证名额为 0 时，岗位自动变为关闭状态。3. 验证 TA 界面状态同步更新。 | 5 | Epic: Application Process
US-11 | Track Status | As a TA applicant, I want to see the status of all my past and current applications in one dashboard, so that I don't have to guess the outcomes. | Should have | 3 | 1. 验证仪表盘准确分类显示 Pending、Accepted 和 Rejected 的记录。 | 3 | Epic: Application Process
US-12 | Admin Dashboard & Reports | As an Admin, I want to view a high-level summary (total vacancies, total applications, filled roles), so that I can monitor recruitment progress. | Should have | 3 | 1. 验证 Admin 界面能动态计算并显示各项总数。2. 验证 Admin 可以查看所有用户的活动状态。 | 8 | Epic: Admin Oversight
US-13 | Admin Workload Report | As an Admin, I want to view a list of all hired TAs and their total accumulated working hours, so that I can monitor the overall school workload. | Must have | 3 | 1. 验证 Admin 面板能汇总计算每个 TA 的总工作时长。 2. 验证能按工作量从高到低排序。 | 5 | Epic:Workload
US-14 | Workload Constraint | As a system, I want to prevent a TA from being 'Accepted' if it causes them to exceed 20 working hours, so that workload regulations are respected. | Should have | 3 | 1. 验证当 TA 总时长将超过 20 时，MO 无法 Accept 并收到系统警告。 | 5 | Epic: Workload&System (NFR)合理的业务边界拓展。
US-15 | Identify Missing Skills | As a TA, I want AI to analyze my profile against a job and identify missing skills, so that I can know what to improve for future applications. | Could have | 4 | 1. 验证 TA 在查看岗位详情时，能点击“AI 分析”。2. 验证 AI 能返回一段文本，明确指出缺失的具体技能。 | 8 | AI Feature提升用户体验。
US-16 | AI Workload Balancing | As an Admin, I want AI to analyze the school's workload distribution and suggest reallocations if some TAs are over-utilized, so that we balance the workload fairly. | Want to have | 4 | 1. 验证 AI 能够读取所有 TA 的 workload 数据。2. 验证 AI 能输出一段负载均衡优化建议。 | 13 | AI Feature属于高阶探索，优先级放低 。
US-17 | AI Skill Matching | As an MO, I want to use an AI tool to match applicants' skills with my job requirements, so that I can quickly identify the most suitable candidates. | Could have | 4 | 1. 验证系统能调用 AI 接口对比 TA Profile 和 Job Description。2. 验证系统能输出一个 0-100 的匹配度分数 (Match Score)。 | 8 | AI Feature需处理结构化 Prompt。